St Joseph’s RC Primary School

PE/Sport Premium Action Plan 2024-2025

Action Plan

Key Improvement Priority: - - The engagement of all pupils in regular physical activity – promoting healthy active lifestyles - - The profile of PE and sport being raised across the school as a tool for whole school improvement - - Increased confidence, knowledge and skills of all staff in the assessment of PE - - Broader experience of a range of sports and activities offered to all pupils - - Increased participation in competitive sport Lead person accountable for the plan: Liam Haveron (PE Coordinator)

| Action | Resources/Costs/Time | Summary of what action will be taken | How will this be monitored? | Success Criteria: How will this action be successful? | Actual impact: What did the action or activity achieve. Review February 2025 Final review in July 2025 |
| --- | --- | --- | --- | --- | --- |
| PE Equipment Audit | Equipment required To be assessed throughout year based on needs of school Allocated- £1000 Initial Autumn spend on - Soft balls for EYFS PE lessons - Storage for PE equipment - Storage for mats Proposed spend May 2025- £1368 | PE coordinator to audit and assess PE equipment already available in school and whether it is suitable for a full PE curriculum | Feedback to SLT and next steps discussed | PE coordinator/Head Teacher to buy necessary equipment. Children to have access to new sports equipment to facilitate play during lessons and at playtime. |  |
| PE equipment storage | £1000 Proposed spend £190 | Appropriate outdoor storage to ensure that yard and PE equipment is kept in a good condition |  |  |  |
| Playground Equipment Audit | Balance equipment Basketball net £500 Spent - Basketball hoops- £132 Proposed spend June 2025- £844 |  |  |  |  |
| Sports Leaders | Training- within SLP SLA Equipment-£60 - Badges - Bibs | Children to be given their new roles and sign contracts agreeing to these roles in school. | - PE coordinator to minute meetings with sports leaders. - PE coordinator and class teacher to monitor their playground roles | Increase in the input of children on decisions made by the head and PE coordinator about sport. Increased responsibility of sports leaders with their duties on the yard. |  |
| Chester-Le-Street football affiliation fees | £150 | Affiliation to Chester-Le-Street FA | LH to liaise with Tom Baker | Children to compete in football leagues and cups |  |
| Derwentside football affiliation | £350 | Affiliation to Derwentside SLA to take part in football leagues | LH to liaise with Tom Baker | Children to compete in football leagues and cups |  |
| Sporting Trophies | £600 30 trophies for Outdoor Education Residential Shield Trophy by Infinity Stars 10cm (4") (trophystore.co.uk) 14 trophies engraved for Year 6 sporting awards Sports day medals Sports Day Medal by Infinity Stars Antique Gold 50mm (2") (trophystore.co.uk) | Trophies and engraving to celebrate the sporting achievements of the children- sports day medals/trophies/engraving | LH to monitor | Motivation of children competing and pupil feedback |  |
| Extra-Curricular coaching | £1500 | After school clubs in the Autumn, Spring and Summer term by REEVO coaching- 2 per week | LH to monitor | Feedback from children and parents on surveys |  |
| Circuit training | £400 | Year 5 circuit training sessions in Spring 2 |  |  |  |
| Basketball curriculum coaching | £1500 | Curriculum basketball coaching for Years 4, 5, 6 |  |  |  |
| Transport | £1000 Residential Bus £700? | Book transport for events | Where possible use staff transport for events but book busses when this isn’t possible. | All children have access to all events regardless of transport |  |
| Outdoor learning trips (Subsidised) | £3000 +£225 to cover disadvantaged +£250 for Gorge walking session | Subsidising the cost of Year 6 Residential trip | Feedback to SLT and PE coordinator | Increased opportunity for children to experience outdoor learning |  |
| Sports Kits | £500 To buy new sporting vests and to replace missing items in current sports kits - Athletics vests - Football kit - black socks - black shorts | Sports Kit to be ordered for sports teams across school | LH to organise | Ensure there are matching kits for all children. Ensure that the school is seen in a positive light at events. |  |
| Staff cover for CPD | £1500 | Covering staff for CPD opportunities. | SLT to organise | Staff will have the opportunity to attend all CPD which they need. |  |
| Staff PE Kits | £300 Staff hoodies/zip ups for PE Staff T-shirts for PE | Cost of subsidised PE kits for staff which include new school badge. | N/A | Staff wearing appropriate clothing will feel more comfortable teaching PE lessons |  |
| PE Planning Scheme | £695 per year Primary PE Planning https://primarypeplanning.com/purchase-membership-plan/ | PE planning scheme for staff to follow which will replace Core Tasks. |  |  |  |
| Reward system for sport and active breaktimes | https://www.tokensfor.com/product/floor-standing-house-token-collector/ £390 https://www.tokensfor.com/product/eco-tokens/ £36.95 x 4 (for each house colour) https://www.tokensfor.com/product/28mm-small-desktop-tubes/ £60 each = £480 |  |  |  |  |
| Survey of Teachers | N/A | PE coordinator to survey teachers on their knowledge and understanding of the PE curriculum as well as their confidence in teaching, planning and assessing. Summer Term 2025 | - Feedback from survey to be analysed by PE coordinator and staff to be offered support in areas where they do not feel confident. - Analysis to be shared with SLT - CPD opportunities to be presented to all staff where possible. | Increase in confidence of teachers when teaching PE |  |
| Survey of Children | N/A | Survey of PE, extracurricular sport and clubs given out to children. Spring 2025 | - PE coordinator to analyse answers from children and discuss any issues with SLT and Sports Leaders. | To further understand the perception of Pe and sport at St. Joseph’s from then point of view of the children. |  |
| September- allocated £15,855 Sports Premium money received: £17,810 |  |  |  |  |  |
| February 2025 review- spent: |  |  |  |  |  |
| July 2025 review- spent: |  |  |  |  |  |